## Slide 1: System Analysis
Section 2

## Slide 2: From Previous Section
Planning
Analysis
Design
Implementation
System Request
Feasibility Study
Project Plan
  Methodology
  Time Estimation
  Task Identification
  Pert Chart
  Gantt Chart
  Scope Management
Interview
JAD Session
Questionnaire
Use Case
Data Flow Diagram
Entity Relationship
Normalization

## Slide 3: Project Methodology
Project methodology is an approach that describes how to implement SDLC.
Examples of Methodology:
  Waterfall Method.
  Parallel Method.
  Rapid Application Development (RAD)
    Iterative Method.
    System Prototyping.
  Agile Development.

## Slide 4: Waterfall Method
Planning
Analysis
Design
Implementation
System
Analysts and users proceed sequentially from one phase to the next.

## Slide 5: Parallel Method
Planning
Analysis
Design
Implementation
System
Design
Design
Design
Implementation
Implementation
Implementation
The project is divided into a series of subprojects that can be designed and implemented in parallel

## Slide 6: Iterative Method (RAD)
Planning
Analysis
Design
Implementation
Analysis
System Version 1
Design
Implementation
Analysis
System Version 2
Design
Implementation
Analysis
System Version 3
Breaks the overall projects into a series of versions that are developed sequentially.

## Slide 7: System Prototyping (RAD)
Planning
Analysis
Design
Implementation
System Prototype
Implementation
System
Performs analysis, design and implementation concurrently in order to quickly develop a simplified version of the proposed system and give it to users for evaluation and feedback.

## Slide 8: Agile Development
Planning
Analysis
Design
Implementation
System
Face-to-Face communication in each phase.

## Slide 9: Time Estimation
To know total project time, use planning time to predict the time required for the entire project.
The percentage of phases time are:
  Planning  15%
  Analysis  20%
  Design  35%
  Implementation  30%

## Slide 10: Task Identification
Its divide project into subtasks and each subtask into subtasks and so on.
Example | Task Information
Economic Feasibility | Name of Task
16-2-2015 | Start Date
20-2-2015 | End Date
Mohamed Gaber | Person assigned to task
High | Priority
Microsoft Word | Resources Needed
10 Hours | Estimated Time
8 Hours | Actual Time

## Slide 11: Pert Diagram (Example 1)
Consider the list of four activities for planning phase:-
Draw the Pert Diagram?
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 5
D | Time Estimation | A,C | 3

## Slide 12: Pert Diagram Example 1 Solution
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 5
D | Time Estimation | A,C | 3
1
2
3
4
A, 2
C, 5
B, 4
D, 3

## Slide 13: Pert Diagram (Example 2)
Consider the list of following activities for planning phase:-
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 2
D | Time Estimation | A, C | 3
E | Task Identification | C | 2
F | Pert Chart | C | 5
G | Gantt Chart | D, E, F | 2

## Slide 14: Pert Diagram Example 2 Solution
Activity | Predecessors
A | -
B | -
C | B
D | A, C
E | C
F | C
G | D, E, F
1
2
3
4
7
5
6
A
E
F
C
B
D
G
Dummy
Dummy

## Slide 15: Gant Chart (Example 1)
Consider the list of four activities for planning phase:-
Draw the Gant Chart?
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 5
D | Time Estimation | A,C | 3

## Slide 16: Gant Chart Example 1 Solution
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 5
D | Time Estimation | A,C | 3
A
B
C
D
2
4
9
12

## Slide 17: Gant Chart Example 1 Solution
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 5
D | Time Estimation | A,C | 3
A
B
C
D
2
4
9
12
Critical Path
B  C  D
Minimum Duration Time = 12

## Slide 18: Gant Chart (Example 2)
Consider the list of following activities for planning phase:-
Activity | Description | Predecessors | Duration
A | System Request | - | 2
B | Feasibility Study | - | 4
C | Methodology | B | 2
D | Time Estimation | A, C | 3
E | Task Identification | C | 2
F | Pert Chart | C | 5
G | Gantt Chart | D, E, F | 2

## Slide 19: Gant Chart Example 2 Solution
A
B
C
D
2
4
6
9
Activity | Predecessors | Duration
A | - | 2
B | - | 4
C | B | 2
D | A, C | 3
E | C | 2
F | C | 5
G | D, E, F | 2
E
G
F
8
11
13

## Slide 20: Gant Chart Example 2 Solution
A
B
C
D
2
4
6
9
Activity | Predecessors | Duration
A | - | 2
B | - | 4
C | B | 2
D | A, C | 3
E | C | 2
F | C | 5
G | D, E, F | 2
E
G
F
8
11
13
Critical Path
B  C  F  G
Minimum Duration Time = 13

## Slide 21: Scope Management
Who will responsible for who?
Project Manager
Senior Analyst
Senior Designer
Senior Developer
Junior Analyst
Junior Analyst
Junior Designer
Junior Designer
Junior Developer
Junior Developer

## Slide 22: SDLC
Planning
Analysis
Design
Implementation
System Request
Feasibility Study
Project Plan
  Methodology
  Time Estimation
  Task Identification
  Pert Chart
  Gantt Chart
  Scope Management
Interview
JAD Session
Questionnaire
Use Case
Data Flow Diagram
Entity Relationship
Normalization

## Slide 23: Task 1 (Solved)
Draw Pert diagram for the following activities:-
Activity | Predecessor
A | -
B | A
C | A
D | -
E | D
F | B, C, E
G | F
H | D
I | G, H

## Slide 24: Task 2
Draw Pert diagram for the following activities:-
Activity | Predecessor
A | -
B | -
C | -
D | A
E | C
F | B, D
G | B, D
H | E, F
I | A
J | G, H
K | E, F

## Slide 25: Task 3
Draw Pert diagram and gant chart for the following activities and find minimum duration for execution:-
Activity | Duration (Days) | Predecessor
T1 | 8 | -
T2 | 15 | -
T3 | 15 | T1
T4 | 10 | -
T5 | 10 | T2 , T4
T6 | 5 | T1 , T2
T7 | 20 | T1
T8 | 25 | T4
T9 | 15 | T3, T6
T10 | 15 | T5 , T7
T11 | 7 | T9
T12 | 10 | T11

## Slide 26: Taske4
A project has been defined to contain the following list of tasks along with their completing duration.
Draw a Pert chart ii. Show the critical path.

## Slide 27: Task 5
Complete Your Project.

## Slide 28
Thank You